## Project Start
Initial Stages of the Project
Last Update: 13th June 21007
Design Team builds the Initial Game Design Document
Initial GDD
Team Meets to agree all standards to be used for the title (Code,Art,Production,Audio etc)
Internal Kick Off Meeting
The Leads build the base standards doco using the Krome Project Template
Team Builds Standards Doco
Once the Full Schedule is available then the revised milestones can be written
Output: Detailed Milestone Doco
Design Team Builds Revised Game Design Document
Revised GDD
Publisher gives feedback on Initial GDD to allow Design Team to build revised version
Publisher Feedback
Producer builds a full project schedule to make sure the project fits the overall timeframe
Output: Project Schedule
Start Point
Design Team Makes Final Revisions Game Design Document
Fully Implemented GDD
Information on how to run a build (grab data, update RKV, grab exe, run build)
Output: How to Run a Build
List of Command Line Arguments that can be used for the gamer
Output: CmdLine Arguments
How to use the Build Machine
Using the Build Machine
An initial TDD is written to give technical details of the intended implementation
Initial TDD
Publisher gives feedback on Initial TDD and requests additional information in specific areas
Publisher Feedback
A revised TDD is written to give improved detail in the areas requested
Fully Implemented TDD
Document showing the complete Production Pipeline
Output: Production Pipeline
Team Specific Version Control Setup
Version Control Doco
Lead Programmer gets the Build Machine up and running
Build Machine Setup
Art Lead Builds Art Standards with leads for each area (Based on Krome Project Template)
Output: Art Standards (General)
Prop Construction Standard
Output: Prop Standard
Character Build/Animation Standard
Output: Char Build/Anim Standard
Coding Standard (Based on Krome Project Template)
Output: Coding Standards
Processes and Procedures for Getting Things Done (Based on Krome Project Template)
Output: Production Standards
Doco Standard & Directory Structure to be used for the project
Output: Doco/Dir Standard
An Initial asset list is created to ensure a clear picture of what's being built
Full Asset List
Initial Prototype is Built
Prototype
Deals with the Initial Implementation Questions and "Proof of Tech". Acts as a springboard for systems to be used during full production.
Internal Approval?
No
Yes
Internal Approval?
Yes
TDD v1.0 Fully Implemented
Output: Full TDD Available
GDD v1.0 Fully Implemented
Output: Full GDD Available
TD2 Project is Setup
Setup ToDo2 Project
Internal Approved?
No
Yes
Production Standards Available
Production Doco
Internal Approved?
No
Yes
Code Standards Available
Code Doco
Internal Approved?
No
Yes
Art Standards Available
Output: Art Doco
Publisher Approved?
No
Yes
Initial Prototype Built and approved
Output: Prototype Available
Publisher Approved?
No
Yes
Project Schedule and Milestone Layout is Available
Output: Project Schedule
Actor Budget defines bone count, poly count, texture types and sizes for all types of actor per SKU
Output: Actor Budget
Prop Budget defines the poly count, texture types and sizes for all types of prop per SKU
Output: Prop Budget
Budget should include bone count for animated props, frag count for fragable props, use of physics primitives
Overall Poly and Texture Budget for level, chunks and vizones is defined in detail
Output: Chunk/Level Budget
Mesh (Level/ Chunk/ ViZone) Construction Standard
Output: Mesh Standard
Include information on use of Physics primitives. Collision mesh poly counts, detailing of collision mesh etc
A brief explanation of how to add physics primitives to props with budget for number of primitives
Output: Physics Intro
Define tools requirements for all areas
Output: Tools Requirements
Define the lighting solution for the game
Output: Lighting Solution
AI, Physics, Materials, Collision, Lighting, Blank areas for Testing Misc
Test Rooms
Shows planned outsourcing workload with asset lists, milestones and budget
Output: Outsourcing Plan
Engine Lead, Art Lead, Producer
No
Publisher Approved?
No
Yes
Engine Lead
All Project Leads
Producer
Publisher Approved?
Yes
No
Engine Lead
All Project Leads
Producer
Internal Approval?
Yes
No
Engine Lead
All Project Leads
Producer
Internal Approved?
No
Yes
Engine Lead, All Project Leads, Producer
Engine Lead, Art Lead, Tech Artist, Art Director, Producer, Code Lead
Engine Lead, Art Lead, Tech Artist, Art Director, Producer, Code Lead
Internal Approval?
Yes
No
Internal Approval?
Yes
No
Engine Lead
All Project Leads
Producer
Engine Lead
All Project Leads
Producer
Bruno: Before design has kicked off I feel that it would be great if the engine team could haveinput into the technical direction for the game. I suggest a meeting where the engine team present possible technical directions or advances that they would like to persue or can make easy gains in. Then design can use this as a springboard for potential game play ideas.
Separate any assets that stand out as being assets that can be outsourced
Outsource Check
Approximate asset list with milestone dates
Output: Outsourcing Asset List
No
Internal Approval?
Yes
All Project Leads
Producer
Example Assets for use to test Outsource Companies with the correct art style
Output: Outsource Art Examples
Outsource Companies are Tested to Find Suitable Team(s) for Project
Outsource Company Tests
Information on outsourceing teams go back to producer (may be publisher approved)
Output: Outsourcing Team(s) Bio
Internal Approved?
No
Yes

## Visual Mesh
Production Schedule
| Planning | Production | Testing
DESIGN | Create a pitch document for the game and a simple 2 page Game Design Document. Plan out a short term production schedule and submit the pitch document and Game Design Document to Jennifer | Have a completed Game Design Document and Beat Sheet Document. Finalise all mechanics and game types present within game | Create a testing plan as well as a google document sheet for people to fill out while testing Arcade Simultator. Assure that all issues are written down and addressed
ART | Begin on creating concept art for the game, create some low poly assets to place within a test scene of Unity. Create a feel for the game | Create fully fleshed out 3D models for the scene and a fully fleshed out 2D pixel art game with assets and models | Polish all in game assets and 2D art. Add more details and fix art according to feedback presented via testing
CODE | Begin to work out how the game will work through C# and Playmaker | Have a complete and working prototype working conveying the main key mechanincs of the game | Fix any bugs or issues that were made present through playtesting. Begin polishing game mechanics.
TIMELINE | 2 WEEKS (Proof of Concept) > | 4 WEEKS (Prototype) > | 7 WEEKS (Playable Prototype) >